## Readiness Chart
Guidelines:
0 ~ 1 (System breakdown; no compliance)
1 ~ 2 (Most of the elements non-existent)
2 ~ 3 (Basic system functioning, results evident)
3 ~ 4 (Systems in place, People understand the intent)
4 ~ 5 (Above the system requirements)
Sl No | Criteria | Current Score
A | Overall Score | 0.0025
1 | General Management / Corporate Governance | 0.05 | Sunder
2 | Health, Safety, Security, & Environment | 0 | Mine
3 | Contract Strategy and Management | 0 | Sunder
4 | Finance / Accounting / Procurement | 0 | Sunder
5 | People | 0 | Sunder
6 | Design Review | 0 | Hammad
7 | Operation and Maintenance | 0 | Hammad
8 | IMS and Risk Management | 0 | Anna
9 | SCADA / IT Cybersecurity / SAP / ENGICA | 0 | Nikhil
10 | Handover & Punch List / Warranty Management | 0 | Nikhil

## Sheet1 (hidden)
General Management / Corporate Governance | Sunder | Maqsood/ Priyadarshi
Health, Safety, Security, & Environment | Mine | Malcolm /Priyadarshi
Contract Strategy and Management | Sunder | Priyadarshi
Finance / Accounting / Procurement | Sunder | Sujith
People | Sunder | Ali Raza/Priyadarshi/Brajesh
Design Review | Hammad | Priyadarshi
Operation and Maintenance | Hammad | Priyadarshi/Brajesh/Maqsood
IMS and Risk Management | Anna | Priydarshi/Maqsood
SCADA / IT Cybersecurity / SAP / ENGICA | Nikhil | Priydarshi/Ali Raza/Maqsood/Malcolm
Handover & Punch List / Warranty Management | Nikhil | Priydarshi/Maqsood/Brajesh

## Checklist Operational Readiness (hidden)
O&M Assesment BENBAN EGYPT
| Weightage | Element Score | Benban Element Score | Ideal Rating | Actual rating | Actual Hassyan Rating | Initial Score | Final Score | Current Status | Hassyan | Action item | Responsible | Target Date
General Management / Corporate Governance (7%) | 4.515% | 0 | 0 | 100 | 0 | 0
Official COD communication and takeover ceritificates | 4 |  |  | 10 | [9 empty] | TRUE
Handover Management | 4 |  |  | 10 | [9 empty] | TRUE
Contract tracker / legal register in place? Any non compliances? | 5 |  |  | 10 | [9 empty] | TRUE
Current operation mode of site | 1 |  |  | 10 | [9 empty] | TRUE
Communication with Project Company | 4 |  |  | 10 | [9 empty] | TRUE | ok
Stakeholder Management | 3 |  |  | 10 | [9 empty] | TRUE
Local government regulation / license requirements and status | 5 |  |  | 10 | [9 empty] | TRUE
Reporting calendar finalized (frequencies, resource requirement, duration for preparation, date of submission,…) From O&M Contract | 2 |  |  | 10 | [9 empty] | TRUE
Insurance compliance in place | 4 |  |  | 10 | [9 empty] | TRUE
5 year Business Plan | 3 |  |  | 10 | [9 empty] | TRUE
Health, Safety, Security, & Environment | 9.481% | 0 | 0 | 210 | 0 | 0 | [7 empty] | TRUE
Government / O&M requirements met | 4 |  |  | 10 | [9 empty] | TRUE | Hse resource hired
HSE Plans, procedures in place | 4 |  |  | 10 | [9 empty] | TRUE
Setting HSSE KPIs and Targets | 3 |  |  | 10 | [9 empty] | TRUE
SLC configurtion, HSE observations raised | 2 |  |  | 10 | [9 empty] | TRUE
Emergency response plans | 4 |  |  | 10 | [9 empty] | TRUE
Medical treatment plans | 4 |  |  | 10 | [9 empty] | TRUE
Fire response setup and plans | 5 |  |  | 10 | [9 empty] | TRUE
HSE trainings and competency management | 4 |  |  | 10 | [9 empty] | TRUE
Cooperation with local fire brigade and ambulance | 4 |  |  | 10 | [9 empty] | TRUE
Traffic Management | 2 |  |  | 10 | [9 empty] | TRUE
Instructions / training- to use fire protection systems (basic fire fighting training for all key staff) | 2 |  |  | 10 | [9 empty] | TRUE
Environmental Mangement Plan | 4 |  |  | 10 | [9 empty] | TRUE
Selection and ordering of all ERT material | 3 |  |  | 10 | [9 empty] | TRUE
Safety Induction Process for new employees | 4 |  |  | 10 | [9 empty] | TRUE | second training given by Gibert
Safety Induction process for visitors | 3 |  |  | 10 | [9 empty] | TRUE
Waste management plan and arrangement | 4 |  |  | 10 | [9 empty] | TRUE
Key management system for PTW | 4 |  |  | 10 | [9 empty] | TRUE
Site team awareness about key management system | 3 |  |  | 10 | [9 empty] | TRUE
Provision of lockout tag out on MV breakers available | 4 |  |  | 10 | [9 empty] | TRUE
PPE and NOMAC uniforms availability | 4 |  |  | 10 | [9 empty] | TRUE
Security management arrangement as per O&M contract | 4 |  |  | 10 | [9 empty] | TRUE | id card control implemented
Contract Strategy and Management | 2.257% | 0 | 0 | 50 | 0 | 0 | [7 empty] | TRUE
contractor management procedure implemented | 3 |  |  | 10 | [9 empty] | TRUE
any mainteanance contracts on site? | 2 |  |  | 10 | [9 empty] | TRUE
Outsourced Services |  |  |  | 10 | [9 empty] | TRUE
Identify all required contracts (LTS's / Support contracts / Call off contracts, etc.….. | 3 |  |  | 10 | [9 empty] | TRUE | Gibert visit arranged. Chint to provide inverter training.
Contractor competency management and other controls as per NOMAC procedure | 3 |  |  | 10 | [9 empty] | TRUE
Finance / Accounting | 2.709% | 0 | 0 | 60 | 0 | 0 | [7 empty] | TRUE
Budget approval and availability as per new NOMAC template | 5 |  |  | 10 | [9 empty] | TRUE
Development of Finance Tools and etc. | 4 |  |  | 10 | [9 empty] | TRUE
Financial monthly reporting and KPI's | 4 |  |  | 10 | [9 empty] | TRUE
Risk Reporting | 1 |  |  | 10 | [9 empty] | TRUE
Local tax or government requirements identified and mechanism in place to address it | 3 |  |  | 10 | [9 empty] | TRUE
Site team aware about budgeting process /templates / profit revenue assumptions | 3 |  |  | 10 | [9 empty] | TRUE
People | 14% | 0 | 0 | 310 | 0 | 0 | [7 empty] | TRUE
Policies and Procedures |  |  |  | 10 | [9 empty] | TRUE
Implement NOMAC HRM procedures and processes | 2 |  |  | 10 | [9 empty] | TRUE
Develop job description and function grades and pay scales | 3 |  |  | 10 | [9 empty] | TRUE
Recruitment |  |  |  | 10 | [9 empty] | TRUE
Labor law compliance | 5 |  |  | 10 | [9 empty] | TRUE
Localization requirements met | 4 |  |  | 10 | [9 empty] | TRUE
Develop approved org chart | 3 |  |  | 10 | [9 empty] | TRUE
people mobilized as per the plan | 4 |  |  | 10 | [9 empty] | TRUE
Develop contract staff strategy (site permanent contractors) | 3 |  |  | 10 | [9 empty] | TRUE
Site team has relevant PV experience ? | 3 |  |  | 10 | [9 empty] | TRUE
Site team has license as per local government regulations | 4 |  |  | 10 | [9 empty] | TRUE
EPC training | [13 empty] | TRUE
Execution / Quality of Planed Training | 4 |  |  | 10 | [9 empty] | TRUE
Site team aware of the training content / comfortable with the O&M | 4 |  |  | 10 | [9 empty] | TRUE
NOMAC Training | [13 empty] | TRUE
Defining NOMAC Training Plan as per Corporate guidelines | 3 |  |  | 10 | [9 empty] | TRUE | gibert provide PV training
Permit accepter training program | 4 |  |  | 10 | [9 empty] | TRUE
Operator / maintenance assessment - demonstrate through interview assessments prior to authorization to operate | 5 |  |  | 10 | [9 empty] | TRUE | done by gibert
SAP ERP training, CMMS/Permit/Finance etc… | 3 |  |  | 10 | [9 empty] | TRUE
Facility management | [13 empty] | TRUE
Arc flash areas marked on site | 3 |  |  | 15 | [9 empty] | TRUE
Admin building and staff offices (quality and any major issues) | 3 |  |  | 15 | [9 empty] | TRUE
Switchgear rooms | 5 |  |  | 25 | [9 empty] | TRUE
Battery rooms | 5 |  |  | 25 | [9 empty] | TRUE
Warehouse | 4 |  |  | 20 | [9 empty] | TRUE
Water tank for refilling of tanker | 4 |  |  | 20 | [9 empty] | TRUE
Parking for cleaning tracter | 4 |  |  | 20 | [9 empty] | TRUE
Design Review | 4.289% | 0 | 0 | 95 | 0 | 0 | [7 empty] | TRUE
Reviews of Initial Spare Parts Lists as per O&M agreement | 4 |  |  | 20 | [9 empty] | TRUE
Equipment FAT Reports Reviews and participation | 5 |  |  | 25 | [9 empty] | TRUE | no major issues as per Gibert
HAZOP Study and review meetings | 5 |  |  | 25 | [9 empty] | TRUE
Arc Flash testing reports availability | 5 |  |  | 25 | [9 empty] | TRUE
Operation and Maintenance | 37.25% | 0 | 0 | 825 | 0 | 0 | [7 empty] | TRUE
Short term and Long Term Operating Plan approval by PC as per O&M contract | 3 |  |  | 15 | [9 empty] | TRUE
O&M manuals from EPC | 3 |  |  | 15 | [9 empty] | TRUE
Finalize the list of O&M Procedures | 3 |  |  | 15 | [9 empty] | TRUE
Identification and availability of high priority procedures (needed at COD) | 5 |  |  | 25 | [9 empty] | TRUE
Operation | [13 empty] | TRUE
Defining of Operation Concept (shifts, modes of operation, operation strategy, Plant area responsibility allocation) | 3 |  |  | 15 | [9 empty] | TRUE
Permit to work and LOTO procedure | 5 |  |  | 25 | [9 empty] | TRUE
Change Management Process (Commissioning and after COD) | 4 |  |  | 20 | [9 empty] | TRUE
Electrical Switching and Isolation procedure (Operation of Electrical Installation) | 4 |  |  | 20 | [9 empty] | TRUE
Handover of Voice/Data recording system for communication with Grid operator | 3 |  |  | 15 | [9 empty] | TRUE
Performance monitoring, evaluation, and reporting process | 4 |  |  | 20 | [9 empty] | TRUE | training provided . SCADA still not able to provide PR numbers etc
Operational Incident Investigation process (RCA/Investigation/Lessons learnt) | 4 |  |  | 20 | [9 empty] | TRUE
Grid / PWPA contract and liaison management | 4 |  |  | 20 | [9 empty] | TRUE
Daily report format and mechanism finalized | 3 |  |  | 15 | [9 empty] | TRUE | ok
ACWA reporting streamlined | 3 |  |  | 15 | [9 empty] | TRUE
Monthly reporting format and process finalized | 3 |  |  | 15 | [9 empty] | TRUE
Annual reporting format and process finalized | 2 |  |  | 10 | [9 empty] | TRUE
Soiling obligation | 5 |  |  | 25 | [9 empty] | TRUE
Weather station PM as per contract | 4 |  |  | 20 | [9 empty] | TRUE | ok
Maintenance |  |  |  | 0 | [9 empty] | TRUE
Major technical issues on site | 5 |  |  | 25 | [9 empty] | TRUE
Standardized maintenance plans available in SAP as per NOMAC corporate guidelines | 4 |  |  | 20 | [9 empty] | TRUE
PV panels cleaning processes and setup as per O&M contract requirement | 5 |  |  | 25 | [9 empty] | TRUE | 2 cleaners need to be hired
Transformer DGA results reviewed on regular basis | 4 |  |  | 20 | [9 empty] | TRUE
PM plans being implemented in field | 4 |  |  | 20 | [9 empty] | TRUE
Necessary arrangements in place for inverter / panel replacement | 4 |  |  | 20 | [9 empty] | TRUE
Earthing / gorunding benchmarking data available | 3 |  |  | 15 | [9 empty] | TRUE
Regular earhing / grounding measurements in place | 3 |  |  | 15 | [9 empty] | TRUE
Thermography checks carried out | 4 |  |  | 20 | [9 empty] | TRUE
Provision of thermography on switchgear, combiner boxes, etc | 3 |  |  | 15 | [9 empty] | TRUE
Arc flash protection suits etc? | 3 |  |  | 15 | [9 empty] | TRUE
Interlock testing records (HV, MV, Transformers, RMU, etc) | 4 |  |  | 20 | [9 empty] | TRUE | done by Gibert
Equipment Labelling (tagging) | 4 |  |  | 20 | [9 empty] | TRUE
Equipment Labelling (as per Plant codification), Voltage Warning labels,… | 3 |  |  | 15 | [9 empty] | TRUE
Alarm Management : Critical Alarms on Equipment and SCADA systems (High Voltage Station and PV farm) | 4 |  |  | 20 | [9 empty] | TRUE
Equipment Panel Doors, Facility Door Keys, Inverter/Transformer Container Keys,… | 2 |  |  | 10 | [9 empty] | TRUE
Reliability of Supply |  |  |  | 0 | [9 empty] | TRUE
Master Equipment List | 3 |  |  | 15 | [9 empty] | TRUE
Criticality Ranking | 5 |  |  | 25 | [9 empty] | TRUE
FMEA analysis | 2 |  |  | 10 | [9 empty] | TRUE
Mitigation Action Plan | 5 |  |  | 25 | [9 empty] | TRUE
Safety Critical Devices | 5 |  |  | 25 | [9 empty] | TRUE
Material Management Process |  |  |  | 0 | [9 empty] | TRUE
Development / approval of Procurement Plan | 4 |  |  | 20 | [9 empty] | TRUE
Establish the site ware house stocking procedure | 4 |  |  | 20 | [9 empty] | TRUE
Spares Management, Consumables , Tools and Equipment's- |  |  |  | 0 | [9 empty] | TRUE
Purchasing of spare parts and storage on site (warehouse or containers) | 5 |  |  | 25 | [9 empty] | TRUE | Done by Oman support
Review Tools list in ISP and Inspection of Tools | 4 |  |  | 20 | [9 empty] | TRUE
Tools management done as per NOMAC corporate procedure | 4 |  |  | 20 | [9 empty] | TRUE
IMS and Risk Management | 2.032% | 0 | 0 | 45 | 0 | 0 | [7 empty] | TRUE
Risk register | 2 |  |  | 10 | [9 empty] | TRUE
Document management system defined and approved | 4 |  |  | 20 | [9 empty] | TRUE
Develop site specific IMS documents (work instructions, plans, procedures) | 3 |  |  | 15 | [9 empty] | TRUE
SCADA / IT Cybersecurity / SAP / ENGICA | 16.7% | 0 | 0 | 370 | 0 | 0 | [7 empty] | TRUE
Communication channels for O&M staff | 4 |  |  | 20 | [9 empty] | TRUE
Local cybersecurity requirements assesed | 5 |  |  | 25 | [9 empty] | TRUE
Cybersecurity compliance status as per AP framework and gov regulations | 4 |  |  | 20 | [9 empty] | TRUE
IPs, Access and Operational Passwords, Setup parameters of the communication devices, etc. | 4 |  |  | 20 | [9 empty] | TRUE
Software applicable and licenses for the software of all equipment (SCADA, Inverters, Electrical Protection Relays, DC rectifiers,…) | 4 |  |  | 20 | [9 empty] | TRUE
Procure, Deliver & Install Hardware & Software including LAN Infrastructure needed for NOMAC IT | 5 |  |  | 25 | [9 empty] | TRUE
IT crisis plan / recovery / back-up (what if) | 4 |  |  | 20 | [9 empty] | TRUE
SAP system design and software installation and setup | 5 |  |  | 25 | [9 empty] | TRUE
SCADA functionality and issues | 5 |  |  | 25 | [9 empty] | TRUE
Security logging and entry system | 4 |  |  | 20 | [9 empty] | TRUE
SAP Master data collection | [13 empty] | TRUE
PM | 1 |  |  | 5 | [9 empty] | TRUE
MM | 1 |  |  | 5 | [9 empty] | TRUE
FICO | 1 |  |  | 5 | [9 empty] | TRUE
PM plans in place | 5 |  |  | 25 | [9 empty] | TRUE
BOM linked | 3 |  |  | 15 | [9 empty] | TRUE
SCD marked in SAP | 5 |  |  | 25 | [9 empty] | TRUE
Criticality analysis in SAP | 3 |  |  | 15 | [9 empty] | TRUE
Engica Training to End Users | 3 |  |  | 15 | [9 empty] | TRUE
ENGICA Implementation | 4 |  |  | 20 | [9 empty] | TRUE
ENGICA PTW Authorization | 4 |  |  | 20 | [9 empty] | TRUE
Handover & Punch List / Warranty Management | 6.772% | 0 | 0 | 150 | 0 | 0 | [7 empty] | TRUE
Punch list management procedure in place | 5 |  |  | 25 | [9 empty] | TRUE
Insurance requirements | 4 |  |  | 20 | [9 empty] | TRUE
Finalized punch list available | 4 |  |  | 20 | [9 empty] | TRUE
Punch List review and sign off EPC>PC>O&M | 4 |  |  | 20 | [9 empty] | TRUE
Establish warranty management process - process for tracking of warranty and claim management | 5 |  |  | 25 | [9 empty] | TRUE
Documentation received checked against planned and delivered (including quality standard) | 3 |  |  | 15 | [9 empty] | TRUE
"As built" drawings, SLD, Logic drawings, etc received | 5 |  |  | 25 | [9 empty] | TRUE
`

## Readiness Checklist
S. No | Task_Name | Weight | Ideal Score | Progresss | Actual Score | Document in the folder
1 | General Management / Corporate Governance | 5% | 1090 |  | 5%
1.1 | Signed copy of O&M Agreement Available- Contract Compliance prepared and being maintained and compliance ensured | 0.09174% | 20 | 100% | 0.09174%
1.2 | NTP issued | 0.04587% | 10 | 100% | 0.04587%
1.3 | Enterprise Risk register established, monitored and updated as required | 4.587% | 1000 | 100% | 4.587%
1.4 | Legal Permit compliance register prepared and maintained for compliance including Local government regulation / license requirements and status | 0.02294% | 5 | 100% | 0.02294%
1.5 | O&M Company registration | 0.06881% | 15 | 100% | 0.06881%
1.6 | Directors appointed (If Applicable) | 0.04587% | 10 | 100% | 0.04587%
1.7 | Reporting calendar finalized (frequencies, resource requirement, duration for preparation, date of submission,…) From O&M Contract | 0.04587% | 10 | 100% | 0.04587%
1.8 | Insurance compliance in place - Workman compensation | 0.04587% | 10 | 100% | 0.04587%
1.9 | 5 year Business Plan | 0.04587% | 10 | 100% | 0.04587%
2 | HSSE Readiness | 20% | 190 |  | 0%
2.1 | HSE Plans, procedures in place | 1.053% | 10
2.2 | Setting HSSE KPIs and Targets | 1.053% | 10
2.3 | Implementation of People Based Safety Program | 1.053% | 10
2.4 | SLC configuration, HSE observations raised in SLC | 1.053% | 10
2.5 | Emergency response plans | 1.053% | 10
2.6 | Medical treatment plans/ Operation of Medical Center Cooperation with local fire brigade and ambulance | 1.053% | 10
2.7 | Fire response setup and plans Instructions / training- to use fire protection systems (basic fire fighting training for all key staff) Cooperation with local fire brigade and ambulance Fire fighting crew mobilized, with all necessary equipment | 1.053% | 10
2.8 | Selection and ordering of all ERT material/spill kit | 1.053% | 10
2.9 | HSE trainings and competency management Safety Induction | 1.053% | 10
2.10 | Traffic Management | 1.053% | 10
2.11 | Environmental Management Plan | 1.053% | 10
2.12 | Waste management plan and arrangement | 1.053% | 10
2.13 | HSE team mobilized and trained | 1.053% | 10
2.14 | Security management arrangement as per O&M contract | 1.053% | 10
2.15 | PPE and NOMAC uniforms availability | 1.053% | 10
2.16 | Safe Systems of Work (Engica) awareness, reinforcement and validation from the fleet | 1.053% | 10
2.17 | Risk Assessment/Surveys (HIRA) | 1.053% | 10
2.18 | PSSR | 1.053% | 10
2.19 | Chemical Management | 1.053% | 10
3 | Contract Strategy and Management | 5% | 30 |  | 0%
3.1 | Contractor management procedure implemented - all required Contracts are identified and implemented (Priority-1) |  | 10
3.2 | LTSA sign off (if applicable)/ Compliance, CP, Payment scheduled are being met |  | 10
3.3 | Contractor competency management and other controls as per NOMAC procedure |  | 10
4 | Finance / Accounting /Supply Chain Management | 5% | 90 |  | 0%
4.1 | Preparing of Material Management Procedure |  | 10
4.2 | Accounting system and implemented, authority matrix defined |  | 10
4.3 | Internal and external Audits are being carried out as per requirement |  | 10
4.4 | TAX/Vat compliance status |  | 10
4.5 | Warehouse readiness - Handover of furnished Warehouse including racks, bins, storage plan for warehouse is prepared |  | 10
4.6 | Verify Initial Spares and ensure that they are delivered and stored appropriately. GRN are prepared in SAP system, storing is done as per NOMAC procedure including tags having photos |  | 10
4.7 | Chemical stores readiness - |  | 10
4.8 | Workshop equipment's installed and handed over |  | 10
4.9 | Procurement Process Set-up - Procurement plan for Spares, Consumables, Contracts are in place |  | 10
5 | People | 10% | 80 |  | 0%
5.1 | Approved org chart (approved by NOMAC, PC approval if needed as per O&M contract) including Permanent contractor staff |  | 10
5.2 | Implement NOMAC HRM procedures and processes - Develop job description and function grades and Hay level |  | 10
5.3 | Labor law compliance |  | 10
5.4 | Localization plan and fulfillment |  | 10
5.5 | People mobilization as per plan |  | 10
5.6 | Site team has relevant technology experience |  | 10
5.7 | Site team has license as per local government regulations (if applicable) |  | 10
5.8 | EPC training- Training conducted as per plan and validation |  |  |  |  | All the employes should get the relevant area training from the EPC / Vendor,
5.9 | NOMAC Training |  | 10
5.9.1 | Defining NOMAC Training Plan as per Corporate guidelines
5.9.2 | Plant Qualification program implementation status - Operator / maintenance assessment -
6 | Design Review | 5% | 40 |  | 0%
6.1 | Master Document List provided/ updated O&M relevant documents reviewed and comments are closed. Open comments tracker available and maintained |  | 10
6.2 | Design Review Documents O&M Comments are submitted |  | 10
6.3 | HAZOP/SPOF/RAM/SIL/Arc flash study/3D review is completed, Quality review and action items are implemented and closed |  | 10
6.4 | Listing of all Open ROS checkpoints design, installation, commissioning in the Technical Risk Register with risk mitigation, action owner and timeline |  | 10
7 | Operation and Maintenance | 20% | 250 |  | 0%
7.1 | Operation and Maintenance Procedure availability |  | 10
7.2 | Grid / PPA contract and liaison management |  | 10
7.3 | Maintenance Programs (MEL Based on KKS, PM task list, Plan, Critical Operation Routines and inspection plan) |  | 10
7.4 | Criticality Ranking, safety critical devices identification & SPOF (as per Corporate Procedure) |  | 10
7.5 | ROS framework V4 Elements Compliance during Mobilization and before COD/Takeover including Checklist, Enhancement Program (as applicable), Corrosion survey report etc. |  | 10
7.6 | SPOF Mitigation Planning action compliance |  | 10
7.7 | O&M Critical System Mitigation |  | 10
7.8 | O&M Lessons Learned review and implementation as applicable, Sign off Compliance sheet |  | 10
7.9 | Sanity Check Electrical Protections (in particular Selectivity on the Interfaces) |  | 10
7.10 | Trip Electrical & Instrument (E&I) list. |  | 10
7.11 | Record of Temporary modifications (MOC As Applicable) |  | 10 |  |  | all drawings and site changes clouded and marked up. This should be followed by issuance of As built documents. No safety critical devices should be bypassed or blinded condition. All temporary site modification, Jumpering should be normalized
7.12 | O&M Budgeting - Forecast and Planning |  | 10
7.13 | ISP readiness, SPOF Spares confirmation |  | 10
7.14 | Maintenance Planning Annual maintenance plan (Mid Term and Long Term) (Preparing Budget) |  | 10
7.15 | Workshop setup (tools, equipment, etc..) including calibration certification as per Tools Management procedure. |  | 10
7.16 | Identification, review and purchase of the required spares, consumables, chemicals, tools and special equipment (apart from the fuel and initial spares and EPC provided tools) |  | 10
7.17 | Building setup (staff offices, workshop, stores, control room, other work offices) |  | 10
7.18 | Equip all new buildings with furniture and fittings (stores/workshop/security/canteen/etc.…) |  | 10
7.19 | Locker rooms / showers (temporary and permanent) |  | 10
7.2 | Stationary/ printers and other office facilities |  | 10
7.21 | Staff amenities - Transport/ Canteen setup |  | 10
7.22 | Special tools Review (required for O&M, parameterization changes etc including Tools for generator rotor removal, Protection testing device, Software license for protection relays, software license for excitation/AVR, interface cables, one notebook etc.) |  | 10
7.23 | Lesson learned reviewed, implemented applicable actions and signed off by PGM |  | 10
7.24 | Chemistry review y after commissioning HRSG (as applicable technology) by appointed expert/consultant |  | 10
7.25 | Insurance recommendation during mobilization and operational projects applicable SCD Operation and Maintenance compliance in place |  | 10
8 | IMS Management | 5% | 20 |  | 0%
8.1 | Defining of Quality System Concept |  | 10
8.2 | Develop IMS Policies & Manual |  | 10
8.3 | IMS Mandatory Procedures review |  | NA
9 | SCADA / IT Cybersecurity / SAP / ENGICA | 5% | 120 |  | 0%
9.1 | All SAP System such As FICO/PM/MM/HCM module are in place |  | 10
9.2 | All systems related to HR such as success factor, salary, leave are in place |  | 10
9.3 | Adequate training has been conducted in SAP for relevant personnel |  | 10
9.4 | Engica PTW System (Engica)Implementation Plan, Training and is functioning as planned |  | 10
9.5 | Engica - Permit room is - Preparation of PTW Offices and Tools, with reorder level |  | 10
9.6 | Preparing of IT Procedure & LAN Infrastructure are in place |  | 10
9.7 | Cybersecurity compliance status (Approved from AP digital the plant network architecture from CS compliance perspective) |  | 10
9.9 | IT crisis plan / recovery / back-up (what if) |  | 10
9.10 | Internet security policy also to include DCS management policy |  | 10
9.11 | Performance management and monitoring system setup |  | 10
9.12 | Security logging and entry system, segregation of entry of authorized personnel in respective areas |  | 10
9.13 | Office IT / DMZ (firewall) / wireless are all |  | 10
9.14 | Commissioning and testing of OPC server including all plant tags and it's connection with AP cloud infrastructure |  | 10
10 | Takeover, Punch List & Warranty Management | 20% | 90 |  | 0%
10.1 | ECC - Erection completion Certification & documentation Handover |  | 10
10.2 | CC- Commissioning Completion Certification & documentation is reviewed and taken over |  | 10
10.3 | Punch list management procedure & Alignment with PC, EPC in place |  | 10
10.4 | Finalized punch list available |  | 10 |  |  | List of Punchlist Closed Or Open. No safety punch list should be open, Punchlist with open items & action plan
10.5 | Establish warranty management process - process for tracking of warranty and claim management as per procedure and alignment with PC and EPC |  | 10
10.6 | Technical Insurance requirements (if applicable) |  | 10
10.7 | As built" drawings or marked up drawings, SLD, Logic drawings, received |  | 10
10.8 | Notification - Commencement of O&M Contractor PTW System |  | 10
10.9 | Technical Risk Register acknoledgment & Review |  | 10
10.10 | Commissioning Spares & Consumables availability (as required) |  | 10
10.11 | Software/patches updated |  | 10 |  |  | Master list of all installed software’s along with log in credential and back up softwares . Ensure that all the software patches are updated and current , any obsolescence to be also noted and captured in risk register. Example of typical software list as annexure
10.12 | Calibration Report |  | 10 |  |  | Calibration Certificates / data where applicable
10.13 | PM & CM carried out so far during commissioning |  | 10 |  |  | PM, CM, equipment history and Spares replaced
10.14 | Statutory certificates with next due date (as applicable before handover) |  | 10 |  |  | Total Operating Hours Accumulated Since Commissioning (Rotating equipment)
10.15 | Total Running/Operating hrs of Rotating equipment Since commissioning - As Applicable |  | 10
| Overall Score | 125% |  |  | 0.25%
Note: